## Slide 1
Status Meeting #6
January 12th, 2020
UAEU transformation:
Design Of Operating Model

## Slide 2: Overall Program

## Slide 3: Summary
Status Report Date | 26 January 2019
Project Status | 
Stream
Rating
Comments
Process
This stream is on track, Core processes SME is engaged to validate student affairs processes and managerial.
OD
Changes to the team are fully implemented. Options report is being finalized and reviewed with HE. Current State assessment report will be submitted for final review this week.
IT
Delays in completing the survey has impacted the schedule and delivery of CSA report. Workarounds are in place to deliver the report this week.
Governance
Governance stream has been improved with Higher Education content and examples. With approval of CSA this week, the stream will be back on track.
All Clear
Within Tolerance
Intervention Required
Overall
Delays in 3 streams of the program has prompted the status to amber. All streams have finalised the first project milestone and undergoing approval walk through (Process architecture and design principles, OD current assessment report, Governance current state assessment, journey prioritization and IT current state assessment). Two actions to recover the schedule are:
1- Complete review all the first milestone deliverables
2- Schedule CX focus groups asap
Schedule | Risk/Issues | Quality | Resources
CX
Scheduling focus groups are delayed – they need to be scheduled asap.

## Slide 4
Project Plan | November | December | January | February | March | April
Customer Journey and Process |  |  |  |  |  | 
Support Functions |  |  |  |  |  | 
Core Functions |  |  |  |  |  | 
Management Functions |  |  |  |  |  | 
Organization Design |  |  |  |  |  | 
Current State Assessment and Benchmarking |  |  |  |  |  | 
Organization Structure Options |  |  |  |  |  | 
Detailing Positional Structure |  |  |  |  |  | 
Develop Job Descriptions |  |  |  |  |  | 
Develop Competency Framework |  |  |  |  |  | 
Develop Staffing Model |  |  |  |  |  | 
Governance |  |  |  |  |  | 
Assessment (committees, TOR, charters etc.) |  |  |  |  |  | 
Design new Governance model |  |  |  |  |  | 
Detailing Phase (Governance manual) |  |  |  |  |  | 
IT |  |  |  |  |  | 
IT Assessment & Strategy (Future State Design) |  |  |  |  |  | 
IT Roadmap |  |  |  |  |  | 
Implementation Planning |  |  |  |  |  | 
Implementation Plan |  |  |  |  |  | 
Our High level Implementation Plan
IT assessment
IT Roadmap
Implementation plan
Refine
Validate
Approve
Approve
Approve
Approve
Refine
Validate
Approve
Refine
Validate
Approve
IT Strategy
Approve
SME Workshop
University Holidays
Legend
New Operating Governance Model Design
New Governance Manual Design & Detailing
Approve
Approve
Review of IT Data points
Today
Design
Current State Assessment
Approve
Validate
Design
Approve
Design
Approve
Validate
Design
Approve
Validate
Develop
Approve
Sign Off
Sign Off
Sign Off
Diagnostic Review of Operating Governance Model
Delays

## Slide 5: Detail Status

## Slide 6: Process
Achievements from previous week
Held meeting with strategy team to discuss the Strategy process architecture including the following process groups:
  Strategy Development & Monitoring
  Strategy Management Office
  Operational Plan Management
  Performance Management and Reporting
  Excellence and Quality Management
Held meeting with UAEU project team to discuss the updated process architecture and submitted the architecture and policy mapping for approval
Shared updated research processes with stakeholders for feedback
Received and incorporated feedback on Facilities processes
Discussed changes that need to be done on procedure and policy manual template
Actions for Next Week
Receive approval on the proposed updated process architecture
Conduct process workshops with IA and Risk
Engage with Academic HR
Conduct process workshop with strategy
Receive feedback from HR on shared processes
Agree on final procedure and policy manual
Receive feedback on the policy mapping
Overall | Schedule | Risk/Issues | Quality | Resources

## Slide 7: Organization Design
Achievements from previous week
Created job description template
Prepared the N-2 organization structure options report
Presented and discussed N-2 org structure options
Initiated the functional roles and responsibilities preparation
Developed job description for the Vice Chancellor
Reviewed UAEU Academic Personnel Policy
Actions for Next Week
Update N-2 organization structure options based on UAEU project team feedback
Present N-2 organization structure options to Chancellor
Submit current state assessment and benchmarking report
Finalize and submit n-2 organization structure options
Initiate the detailing of the organization structure
Continue with functional roles and responsibilities preparation
Overall | Schedule | Risk/Issues | Quality | Resources

## Slide 8: Governance
Achievements from previous week
Conducted 3 deep dive sessions with SME Governance to discussed and validated draft of current state assessment, benchmarking and Recommendation Report:
Presented the key findings of governance stream in the Steering Committee
Actions for Next Week
Discuss and validate the current assessment report including recommendations with TMO team
Start working on Draft Charters of Board and Board Committees
Overall | Schedule | Risk/Issues | Quality | Resources

## Slide 9: Information Technology
Achievements from previous week
Received FQTQ responses to applications assessment survey. however a number of responses are yet to be received (Functional – 14; Technical – 3)
Conducted meeting with TPO (Mr. Junaid) to address concerns about the FQTQ surveys and align on the current state assessment process
Ongoing alignment the current state assessment deliverable with transformation workstreams
Further developed the IT current state assessment report covering DoIT budget analysis
  Continued to collate and analyze identified IT gaps and pain-points from IT and non-IT meetings and workshops
Actions for Next Week
Discuss the IT current state assessment report to TPO , and align on key findings
Follow up with TPO on pending FQTQ survey results and requested salaries data
Conduct alignment meetings with key stakeholders across DoIT (including but not limited to applications, infrastructure, support and admin) to validate current state key findings
Continue to engage IT SME to validate assessment and benchmarking findings and obtain further insights on higher-education specific leading practices
Initiate the design phase by preparing the relevant deliverable outline
Overall | Schedule | Risk/Issues | Quality | Resources

## Slide 10: Customer Experience Design
Achievements from previous week
  Presented the personas selection approach and findings to TPO team and received feedback (e.g. dedicated researcher, TAs)
  Developed 6 personas for which customer journey maps shall be designed
  Agreed on including alternative experiences for touchpoints that vary for customers of different sub-drivers (e.g. international students)
  Requested the formation of the focus group with nominated UAEU customers
  Developed focus group guides, questionnaire and hypothesis to be discussed and validated with the focus group participants
Actions for Next Week
  Obtain approval on the developed customer personas for which the target journey will be designed
  Receive UAEU confirmation on the establishment of the focus group with the nominated UAEU customers covering:
    Students
    Alumni
    Researchers
    Faculty
  Conduct co-creation design focus group sessions
  Commence the customer journeys design for the agreed personas
Overall | Schedule | Risk/Issues | Quality | Resources

## Slide 11: Issue Log
# | Brief Description | Date Raised | Raised by | Mitigation Measure | Status
1 | Finalize the engagement contract | 15/12/2019 | Overall program |  | Closed
2 | Finalize the team structure incorporate the feedback received from TMO - The experience and capabilities of Governance and Organization Design Work-streams requires uplift | 16/12/2019 | Noura | Mitigation changes proposed are: OD: Addition of stream lead (Saad Araabi from January) Engaged further senior leadership Mohamad Sbeiti Governance: Increased senior leadership time (Maryam) | Open
3 | Focus groups discussions are delayed due to misalignment of Senior Stakeholders and lack of understanding of CX design process | 22/01/2020 | Tarafa Homsy | Finalize the CX focus groups by end of Sunday | Open

## Slide 12: Risk Log
# | Brief Description | Probability | Impact | Risk Score | Action Plan | status
1 | Availability of process owners and champions significantly impacts on the project timelines | Low | High | 1 | Ensure stakeholders are involved and available to the program 100% | Open
2 | If team mobilization is delayed, overall project timelines will be at risk | Medium | High | 2 | Ensure team is fully mobilized by the end of the week | closed
3 | Due to the volume of the core process, validation session with college operations may take longer than planned. | Medium | High | 2 | Engage earlier with the college Deans and communicate earlier on the process architecture, design principles and draft of process maps. | Closed
4 | In the absence of dedicated governance department, identification of stakeholders and obtaining existing governance information may take longer than planned | Medium | High | 1 | Ensure strategy and impact assessment of strategy is delivered on-time | Closed
5 | SMEs from Higher Education Institutions are not on ground, and they are needed in all work streams to ensure that all conducted work is within the context of the university | Low | High | 1 | Confirmed SME’s: Paul Griffith: Higher Education Transformation SME & Program Director Professor Babak Abbasi: Teaching, Research and Curriculum management 5-15th Jan Mandeep Sudhi: IT HE SME – Throughout January offshore | Closed
6 | If the CX focus group are delayed then there will be an impact on delaying Process Stream | Medium | Medium | 2 | Finalize the CX focus groups by end of Sunday | Open
Rating: 1 : Low 2 : Medium 3 : High

## Slide 13: Risk Log
# | Brief Description | Probability | Impact | Risk Score | Action Plan | status
7 | Risk: Designing an Organization structure for current not the future state. | Low | High | 1 | Ensure the design is driven by the long-term strategy and new operating context of the university. | Open
8 | Risk: Finalizing the solid business case for the OD options on time | Medium | High | 2 | Need continuous follow-up with KPMG and verification of the business case content. | Open
9 | Risk: Confidentiality | Medium | High | 2 | KPMG are not to speak to anyone from UAEU about the OD options except concerned OD stream team. OD stream team and Transformation Team to limit discussing and sharing information about the work in this stream. | Open
10 | Risk: CAA Re-licensure: Commitment to Accreditation Committee and Risk Management Office Director, to deliver Risk Management related processes and policies by end of January. (UAEU deadline is to respond to CAA is mid-February) | Medium | High | 1 | Risk Management Process workshop will be conducted on Monday 27th January. Need to finalize draft processes flowcharts, process manuals and policy manual by 10th February. | Open
11 | Concern: Management Processes have yet not been reviewed for validity and comprehensiveness | Low | High | 1 | The team to benchmark proposed processes with reference models to identify gaps in processes. | Open
12 | In a hurry to submit all the journeys and close the CX stream | Medium | Medium | 2 | Focus group sessions will not be conducted unless we ensure that the right Personas will be covered by the team | Open
13 | CX team can’t proceed with conducting any focus group sessions with students without obtaining security clearance as per the university policies and procedures. | Medium | Medium | 2 | Request of security clearance was submitted a week ago and awaiting to receive confirmation from the HR department. Start with focus group sessions related to faculty and industry partners until clearance is obtained. | Open
Rating: 1 : Low 2 : Medium 3 : High

## Slide 14: Risk Log
# | Brief Description | Probability | Impact | Risk Score | Action Plan | status
14 | Report not capturing the academic nature of the university | Low | High | 1 | Ensure the Paul Griffith is leading the review of the Governance Assessment Report and involvement in developing the remaining governance deliverables. | Open
15 | Missing Stream Lead of Governance | Medium | High | 2 | Ensure a qualified stream lead is on the ground to lead the progress with the governance stream in absence of Maryam Zaman. | Open
16 | Lateness in finalizing the current IT assessment | Medium | High | 2 |  | Open
17 | Acquiring and implementing new software in different functions in the university | Medium | High | 1 | To be discussed with KPMG | Open
18 | Clarity of ownership of Research Processes | Low | High | 1 | To meet the Provost and discuss with him the available options | Open
19 | Influence of Process owners of Teaching Processes | Medium | Medium | 2 | To expand the discussion to a wider audience and incorporate their feedback | Open
Rating: 1 : Low 2 : Medium 3 : High

## Slide 15: Meeting Actions (No action pending)
# | Action Description | Date Raised | Raised by | Status
1 | Amir and Sherif to review the plan by end of the day 24th and finalize the plan Update: Plan was reviewed and a risk on College processes identified. Activities for January are being modified to accommodate for the mitigation plans | 24/11 | Amir | Closed
2 | Amir and Sherif to review and ensure the status report is aligned prior to Sunday weekly status update meetings | 24/11 | Ashraf | Closed
3 | UAEU to send KPMG the new drafted Laws and KPMG to review and advise on potential impact on the operating model | 24/11 | Ashraf | Closed
4 | Add Time/Resource/Quality/Risk and issue indicator to the status report | 22/12 | Ashraf | Closed
5 | Add Sign Off activities to the process plan | 22/12 | Ashraf | Closed
6 | Share and review procedure template with Sherif and the PMO team | 22/12 | Ashraf | Closed
7 | Organize 2 deep dive sessions on OD assessment and Process design principle: Deep dives been completed. Further sessions required | 22/12 | Ashraf | Closed
8 | Provide feedback from review of the University law – Due by 6/01 | 22/12 | Ashraf | Closed
9 | Provide feedback on the HR policies – Due 7/01 | 22/12 | Sherif | Closed